## Sheet1
Defect ID | Sumamry | Detected By | Defect date | Assign To | Severity | Priority | Status | Build Version | Module | Environment | Defect Type | Reproduceable | Reproduce Steps | Expected Result | Acual Resut | Comment
DEFECT_01 | In Galleries Best Kitchen Pictures are can not be seen by user | Manisha Sarola | 2023-04-15 | developar | low | medium | open | 1 | Galleries | UAT | Funtionality | yes | 1. Open Flipkey.com 2. click on Galleries 3.Best Kitchens 4. view Galleries | When we click on view gallary module pictures can be see to users. | pictures are not see | fail
DEFECT_02 | In Galleries Coolest pool Pictures are can not be seen by user | Manisha Sarola | 2023-04-16 | developar | low | medium | open | 1 | Galleries | UAT | Funtionality | yes | 1. Open Flipkey.com 2. click on Galleries 3.Cooles pool 4. view Galleries | When we click on view gallary module pictures can be see to users. | pictures are not see | fail
DEFECT_03 | logo futionality | Manisha Sarola | 2023-04-17 | developar | medium | medium | open | 1 | logo | UAT |  | yes | 1. Open Flipkey.com 2. click on LOGO | When we click on logo , home page should open , an on home page when we click on logo , wallpaper is change | not on all apge logo is working | Fail